## General Data
General Data
Title | Start Date
Sponsor / Champion | Latest Upate
Team Leader | Team Members
Location/Plant/Site
Org.Unit
Source Of Defect
Process of Production issue
Re-Occurrence
Reference A3
Note on A3: Title/Problem Statement: describes the part/process and the defect: xx_xx_xx_xx_xxxx ( FF_ Project_ Product_ Process_ Problem ) e.g : SAM_Suzuki YP6_ACU_Selective Soldering_Wrong Capacitor issue SAM_SGM SDM41_ACU_SW_Wrong Configuration issue
Note on G10: Function
Note on J10: Name
Note on E13: CCQ_AN CCQ_SAM CCQ_SMY
Note on E16: Quality IE NPL Production SCM IT
Note on E19: Supplier Development Customer Production Logistic NTF Defect Not Identified Under Analysis
Note on E22: SMT_Laser Marking SMT_Printing SMT_Mounting SMT_Reflowing SMT_Operation SMT_Inspection SMT_Others ASSY_De-panel ASSY_ICT ASSY_Flash ASSY_Potting ASSY_Screwing ASSY_Selective Soldering ASSY_Coating ASSY_Press Fit ASSY_Temperature Testing ASSY_Assembly ASSY_EOL ASSY_Other Packing Others
Note on E25: Yes No
Note on E28: Copy reference A3 link or Input A3 ID

## A_Describe Problem
A. Describe Problem / Issue | [5 empty] | Completed
History / Background / Symptom Description
> Customer : |  |  |  | Attachment :
> Project :
> Product :
> Part Number : |  |  |  | Image :
> Problem Type :
> Failure Qty/Rate :
> Occurrence Date :
> Symptom Description :
-
-
-
Problem Description / Current Condition
-
-
-
-
Containment Action
- |  |  |  | Attachment :
-
| Raw Material | Production Line | Warehouse | 3rd Party Warehouse |  | Customer Stock
Activities
Responsibility
Status
Risk Assessment
- |  |  |  | Attachment :
-
Factor |  | Description |  |  | Probability | Funtionally | Safety Relevant
-
-
-
Goal Statement / Target Condition
-
-
Note on B1: Initial step of Structured Problem Solving. Collect facts to describe the Problem and it's background. Describe the target of the Structured Problem Solving activity.
Note on J1: Ongoing Completed
Note on D2: Describe history/background of the issue chronologically and provide a detailed symptom description. Upload pictures to visualize the issue and documents to add detailed information and data.
Note on E3: FAW-VW SVW SGM WDHAC GHAC BBAC FORD GEELY GAC SAIC ......
Note on J3: Attach the document / figure / Diagram for details for eash understanding in case of the complex case
Note on E4: SDM41 VW50 STAR22 SWEET400 Speed XSII TG1D EVO IDB 1.5 ......
Note on E5: ACU IBS CPS CSM IDB BCM DCU TPMS LCU ......
Note on E6: A2C*********/ Customer P/N
Note on J6: Attachment failure pictures
Note on E7: Incoming Failure Production Failure 0-km Failure Field Failure ProtoType Failure
Note on E8: Describe how many quantity about the failures or failure rate
Note on E9: Input the date when the incident occurring
Note on J11: When/Where/Who/What/Why/How : Clear describe the problem , and what's the symptom in the production or in the customer vehicle
Note on D14: detailed information about the problem - fact based understanding of the problem - summarizes relevant information - Update the situation based on the progress at supplier / production / customer side
Note on B19: Start immediate and temporary measures to minimize the impact of the problem at customers and suppliers until a permanent corrective action has been implemented and validated. Sometimes the containment action is not 100% effective. The focus is only on the symptom and not on the root cause of the problem. Typically the root cause is not known at this time. The effectiveness of the containment action should be monitored. As more is learned about the problem, the containment may be improved to address cause(s).
Note on J20: If possible to list a table to summarize the suspicion stock in all areas
Note on B22: In Normal Stock Block Stock On the transit way
Note on D22: Semi-Product Finish Good Rework/Analysis Area Non-Complete box Area Block Area Sample Stock
Note on F22: Storage Bin Block Stock
Note on H22: On the transit way In the normal stock Block Stock/Isolation Area
Note on J22: On the transit way Customer Part Warehouse Customer Line Customer Vehicle Stock Customer Field
Note on B24: Ongoing Completed N/A
Note on D25: Ongoing Completed N/A
Note on F25: Ongoing Completed N/A
Note on H25: Ongoing Completed N/A
Note on J25: Ongoing Completed N/A
Note on C26: Likelihood of issue (e.g. Weibull distribution) Controllability / detectability of issue (e.g. warning signal, handling of problem) Impact of the issue like impact of Continental’s delivery scope on customer’s system or impact of vehicle on environment (source: OEM) Safety relevance of issue yes / no
Note on J27: If possible to list a martix or formula to calculate the risk / potential failure rate
Note on I29: Low Medium High
Note on J29: Low Medium High
Note on K29: Yes No
Note on C33: Understanding the goal is vital to successful problem solving (No goal, No achievement) Clearly define: - How can you measure the problem? (KPI‘s) - When is the problem considered solved? - What is an acceptable KPI? - Set clear and realistic goals. - Keep it SMART (Specific, Measurable, Attainable, Relevant, Time-bound)

## B_Root Cause
B. Find Root Cause of Problem / Issue | [5 empty] | Completed
Identified Causes
o Failure Description
- Method
o ------- o ------- o -------
- Man
o ------- o ------- o -------
- Material
o ------- o ------- o -------
- Measurement
o ------- o ------- o -------
- 'B_Root Cause'!'B_Root Cause'!D14
o ------- o ------- o -------
- Machine
o ------- o ------- o -------
Varified Causes
| Category | Title |  | Verifiy Result |  | Status
Technical and systemic Why-Why for Verified Cause(s)
| Why-1 |  | Why-2 | Why-3 | Why-4 | Why-5
Occurrence
Detection
Systemaic
Note on D1: Perform root cause analysis using proven methods like Fishbone Diagram and Why-Why Analysis. Mandatory for final approval: at least one identified and verified cause and one root cause. There are two levels of root causes: Technical Root Cause The initiating cause that led to the occurrence of the problem (Occurrence)? or the failure to detect the problem (Detection) When eliminated the situation returns to an acceptable status. Systemic Root Cause The failure in our “system” (e.g. processes, organization, standards, design rules, mindset etc.) that allowed the problem to occur or failed to detect the problem. Typically identified by following questions: - Why did our system allow the technical problem to occur? - What was the weakness in our system? - When eliminated, the same (or similar) problem cannot occur again
Note on J1: Ongoing Completed
Note on B2: Compile a list of all potential causes of a problem. Identified causes can be shown and entered in Tree View or Fishbone View. If you switch between them, the data is always the same. The Fishbone Diagram (also called Ishikawa Diagram or Cause and Effect Diagram) is a brainstorming method used to identify potential causes of a problem. The Fishbone diagram is created by a cross-functional team of experts. Causes can be structured by using standard 6M categories or other categories selected by the team. You can use the button to create the 6M categories automatically or you can define your own categories. The Fishbone gives an overview of causes on the highest level, if there are sub causes, the specific cause is marked with a small icon. To see and work on all sub-causes (all levels) use the Tree view. It is possible to create multiple Fishbone Diagrams.
Note on B16: Compile a list of all potential causes of a problem. Identified causes can be shown and entered in Tree View or Fishbone View. If you switch between them, the data is always the same. The Fishbone Diagram (also called Ishikawa Diagram or Cause and Effect Diagram) is a brainstorming method used to identify potential causes of a problem. The Fishbone diagram is created by a cross-functional team of experts. Causes can be structured by using standard 6M categories or other categories selected by the team. You can use the button to create the 6M categories automatically or you can define your own categories. The Fishbone gives an overview of causes on the highest level, if there are sub causes, the specific cause is marked with a small icon. To see and work on all sub-causes (all levels) use the Tree view. It is possible to create multiple Fishbone Diagrams.
Note on B18: Method Man Material Measurement Milieu Machine
Note on C18: From above identified causes
Note on J18: Not Relavant -- Green Suspicion/Possible Reason --- Yellow Confirmed Reason --- Red
Note on F27: The Why Why analysis focuses on two key areas: Occurrence – Focus on the process when the defect was produced - Why did the process create the defect? - Why did we produce the defect? What was the fundamental cause? Detection/Escape – Focus on the process after defect was produced - Why was the defect not detected? Why was it shipped? How did it escape? - Why didn’t the control plan protect the customer from the defect? Steps: 1. Start Why-Why for each verified cause 2. Ask Why as many times as needed to find the Technical Root Cause (for Occurrence and Detection) 3. Verify the identified Technical Root Cause 4. Use Technical Root Cause as starting point for Systemic Root Cause Analysis 5. Process with Why-Why to find the Systemic Root Cause (for Occurrence and Detection) 6. Verify the Systemic Root Cause Dimensions of Systemic Root Causes: - Process / Standard? - Rule / System? - Organization? - Communication? - Mindset / Capability? - Philosophy / Culture?

## C_Solve Problem
C. Solve Problem / Issue |  |  |  |  | Completed
Corrective Action(s)
| Title | Activities | Attachment | Resp. | Due Date | Status
Note on C1: Collect possible solutions and implement the best to cover the technical root cause. Mandatory for final approval: at least one Identified Solution & Verified and Implemented Corrective Action – Detailed Description of Solution(s)
Note on D1: Perform root cause analysis using proven methods like Fishbone Diagram and Why-Why Analysis. Mandatory for final approval: at least one identified and verified cause and one root cause. There are two levels of root causes: Technical Root Cause The initiating cause that led to the occurrence of the problem (Occurrence)? or the failure to detect the problem (Detection) When eliminated the situation returns to an acceptable status. Systemic Root Cause The failure in our “system” (e.g. processes, organization, standards, design rules, mindset etc.) that allowed the problem to occur or failed to detect the problem. Typically identified by following questions: - Why did our system allow the technical problem to occur? - What was the weakness in our system? - When eliminated, the same (or similar) problem cannot occur again
Note on J1: Ongoing Completed
Note on C2: ocument and track action items for verification and implementation of solution. Verification provides proof of the effectiveness of the solution BEFORE implementation. There are actually several verification activities in problem solving: - Verification of the potential causes - Verification of root causes - Verification that a potential solution will be effective before the solution is actually implemented Press the button to assign a new Corrective Action Upload pictures to visualize the action and documents to add detailed information and data.

## D_Validate Solutions
D. Validate Solution and Standardize |  |  |  |  | Completed
Effect Confirmation
| Title | Activities | Attachment | Resp. | Due Date | Status
Read Across/ Preventive Action / Lessons Learned
| Title | Activities | Attachment | Resp. | Due Date | Status
Note on D1: Perform root cause analysis using proven methods like Fishbone Diagram and Why-Why Analysis. Mandatory for final approval: at least one identified and verified cause and one root cause. There are two levels of root causes: Technical Root Cause The initiating cause that led to the occurrence of the problem (Occurrence)? or the failure to detect the problem (Detection) When eliminated the situation returns to an acceptable status. Systemic Root Cause The failure in our “system” (e.g. processes, organization, standards, design rules, mindset etc.) that allowed the problem to occur or failed to detect the problem. Typically identified by following questions: - Why did our system allow the technical problem to occur? - What was the weakness in our system? - When eliminated, the same (or similar) problem cannot occur again
Note on J1: Ongoing Completed
Note on C2: Evaluation of the situation before implementation vs. after implementation - Collect data to compare situation before implementation versus after implementation - Watch for any potential negative effects - Comparison of results with objectives: have the goals been reached? If not, review the root cause, the solution and the implementation. - Description of the solution’s benefits - Upload pictures to visualize the effect confirmation and documents to add detailed information and data.
Note on E15: Preventive Action: Comprehensive change to improve our system and prevent future technical issue (e.g. Rule update, FMEA, Control plan,…) Read Across : extend to the same process / area Lessons Learned : Share with other FFs or locations

## Summary
A3 - Structured Problem Solving
ID: | Title:
Location / Plant / Site |  | Sponsor / Champion | Team: | Start Date: | Latest Update
Org. Unit |  | Author / Team Leader |  | Approval Date: | Approved by: